Clayton Greenwell

Prof. Nasim Anousheh

DSCI D699 Independent Study

24 March 2026

Brief Work Plan for Independent Study (Summer 2026)

Overview: My research idea is to analyze how countries have altered defense spending in the aftermath of the 2022 invasion of Ukraine using various data science tools and techniques. I plan to use World Bank and SIPRI Arms Transfer data to compare historic military expenditures as a percentage of GDP to recent trends.

Some baseline ideas of where this will go:

- Visualize geographical data with Tableau, Seaborn, or Matplotlib.

- Compare World Bank data or SIPRI Arms Transfer data with UN Security Council voting patterns to create country clusters (k-means clustering) of areas moving in the same direction (like the Baltic states).

- Use Time Series Analysis or linear regression to look at where military spending as a percentage of GDP will be in a few years if current trends continue.

My mentor Prof. Nasim Anousheh and I have started a github repository where we are keeping and sharing articles related to the subject.

Outcome: Longform Paper/Jupyter Notebook to be shared on a project portfolio website to be viewed by prospective employers.

This paper/notebook will include:

- Imported csv data

- Data visualizations

- A thesis or hypothesis that is fleshed out with a considerable amount of written analysis.

Hours Per Week on Project: 10 – 14

Number of Required Meetings Between Mentor (Prof. Nasim Anousheh) and Student:

5 Zoom Meetings

List of Milestones with Dates:

Week 1, May 12-17:

- Read “A dynamic separable network model with actor heterogeneity: An application to global weapons transfers”

- Read “The Gravity of Arms”

- Explore all SIPRI arms transfer data

- First Meeting with Mentor

Week 2, May 18-24:

- Read: “Defense Spending, Conflict and Economic Growth in Europe”

- Read “Defence Spending in the European Union: Evolution and Perspectives”

- Explore all World Bank data

Week 3, May 25-31:

- Read: “NATO defense demand, free riding, and the Russo Ukrainian war in 2022”

- Read “Free riding in NATO after the Rise of Russia: cost sharing, free riding and selective incentives in NATO from 2009 to 2019”

- Now that I’ve consumed a pretty large amount of content, I present to my mentor a draft snapshot of

  - What direction/ hypothesis/ thesis I’ll be going with

  - Which of the data I’ll actually use from what I’ve explored (specific World Bank and/or SIPRI Arms Transfer data)

  - What visualizations I’m looking to create with that data

  - What logical frameworks or models I’ll be incorporating into my paper if any (i.e. Heckman selection model or “dynamic separable network model with actor heterogeneity”)

- Second meeting with Mentor

Week 4, June 1-7:

- Read: “Decision-making in the United Nations General Assembly: A comprehensive database of resolution-related decisions”

- Read “The UN General Assembly Voting Coincidence and Clustering Analysis”

- Begin first draft of paper

Week 5, June 8-14:

- Read “Military Expenditure and Economic Growth: A Survey”

- Read “Forecasting Military Expenditure”

- Share first visualization with mentor (can be a draft)

Week 6, June 15-21:

- Read “The Return of the West”

- Read “Measuring Geopolitical Risk”

- Share second visualization with mentor (can be a draft)

Week 7, June 22-28:

- Read “Data and Analyses of Voting in the UN General Assembly”

- Read “Estimating Dynamic State Preferences from United Nations Voting Data”

- Third meeting with Mentor

- Turn in First Draft of Paper

Week 8, June 29 - July 5:

- Read “Bloc Politics at the UN: How Other States Behave When the United States and China–Russia Disagree”

- Read: “Explaining destinations and volumes of international arms transfers: A novel network Heckman selection model”

- Receive Mentor feedback from first draft

- Begin Second Draft of Paper

Week 9, July 6-12:

- Read “Trends in World Military Expenditure, 2022”

- Read “Developments in Military Expenditure and the Effects of the War in Ukraine”

- Continue work on Second Draft of Paper

  - Incorporate in any new perspectives gleamed from additional readings

  - Incorporate in any new perspectives gleamed from mentor feedback

Week 10, July 13-19:

- Read “Meta-analysis of determinants influencing military expenditure”

- Fourth Meeting with Mentor

- Turn in Second Draft of Paper

Week 11, July 20-26:

- Receive second round of feedback from mentor

- Begin final adjustments to paper

Week 12, July 27-31:

- Final fifth meeting with Mentor

- Turn in Final Paper